## Gantt Chart- as of 2_14_2025
Board - Gantt Chart: Savoonga
|  |  | Jan-2025 | Jan-2025 | Feb-2025 | Feb-2025 | Feb-2025 | Feb-2025 | Feb-2025 | Feb-2025 | Feb-2025 | Feb-2025 | Feb-2025 | Feb-2025 | Feb-2025 | Feb-2025 | Feb-2025 | Feb-2025 | Feb-2025 | Feb-2025 | Feb-2025 | Feb-2025 | Feb-2025 | Feb-2025 | Feb-2025 | Feb-2025 | Feb-2025 | Feb-2025 | Feb-2025 | Feb-2025 | Feb-2025 | Feb-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Mar-2025 | Apr-2025 | Apr-2025 | Apr-2025 | Apr-2025 | Apr-2025 | Apr-2025 | Apr-2025 | Apr-2025 | Apr-2025 | Apr-2025 | Apr-2025 | Apr-2025 | Apr-2025 | Apr-2025 | Apr-2025 | Apr-2025 | Apr-2025 | Apr-2025 | Apr-2025 | Apr-2025 | Apr-2025 | Apr-2025 | Apr-2025 | Apr-2025 | Apr-2025 | Apr-2025 | Apr-2025 | Apr-2025 | Apr-2025
| Start | End | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
Status - Done |  |  | 30: Status - Done
Team Code of Cooperation (All) | 30-Jan-2025 | 02-Feb-2025 | 30: Team Code of Cooperation (All) (30-Jan-25 - 02-Feb-25); 31: Team Code of Cooperation (All) (30-Jan-25 - 02-Feb-25); 1: Team Code of Cooperation (All) (30-Jan-25 - 02-Feb-25); 2: Team Code of Cooperation (All) (30-Jan-25 - 02-Feb-25)
Gantt Chart (Shifan) | 02-Feb-2025 | 2025-04-25 | 30: Gantt; 31: Chart; 1: (Shifan); 2: (02-Feb-2025 to 25-Apr-2025); 14: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 15: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 16: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 17: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 18: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 19: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 20: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 21: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 22: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 23: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 24: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 25: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 27: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 28: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 29: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 30: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 31: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 1: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 2: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 3: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 4: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 5: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 6: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 7: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 9: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 10: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 11: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 12: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 13: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 14: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 15: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 16: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 17: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 18: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 19: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25); 20: Gantt Chart (Shifan) (02-Feb-25 - 14-Feb-25)
Population Identification (Alex, Shifan, Terra) | 05-Feb-2025 | 10-Feb-2025 | 5: Population Identification (Alex, Shifan, Terra) (05-Feb-25 - 10-Feb-25); 6: Population Identification (Alex, Shifan, Terra) (05-Feb-25 - 10-Feb-25); 7: Population Identification (Alex, Shifan, Terra) (05-Feb-25 - 10-Feb-25); 8: Population Identification (Alex, Shifan, Terra) (05-Feb-25 - 10-Feb-25); 9: Population Identification (Alex, Shifan, Terra) (05-Feb-25 - 10-Feb-25); 10: Population Identification (Alex, Shifan, Terra) (05-Feb-25 - 10-Feb-25); 17: SPRING; 18: BREAK
Defining Problems (Alex, Ryan, Terra, Shifan) | 07-Feb-2025 | 12-Feb-2025 | 7: Defining Problems (Alex, Ryan, Terra, Shifan) (07-Feb-25 - 12-Feb-25); 8: Defining Problems (Alex, Ryan, Terra, Shifan) (07-Feb-25 - 12-Feb-25); 9: Defining Problems (Alex, Ryan, Terra, Shifan) (07-Feb-25 - 12-Feb-25); 10: Defining Problems (Alex, Ryan, Terra, Shifan) (07-Feb-25 - 12-Feb-25); 11: Defining Problems (Alex, Ryan, Terra, Shifan) (07-Feb-25 - 12-Feb-25); 12: Defining Problems (Alex, Ryan, Terra, Shifan) (07-Feb-25 - 12-Feb-25)
CCCD Assignment (Terra) | 05-Feb-2025 | 16-Feb-2025 | 5: CCCD Assignment (Terra) (05-Feb-25 - 16-Feb-25); 6: CCCD Assignment (Terra) (05-Feb-25 - 16-Feb-25); 7: CCCD Assignment (Terra) (05-Feb-25 - 16-Feb-25); 8: CCCD Assignment (Terra) (05-Feb-25 - 16-Feb-25); 9: CCCD Assignment (Terra) (05-Feb-25 - 16-Feb-25); 10: CCCD Assignment (Terra) (05-Feb-25 - 16-Feb-25); 11: CCCD Assignment (Terra) (05-Feb-25 - 16-Feb-25); 12: CCCD Assignment (Terra) (05-Feb-25 - 16-Feb-25); 13: CCCD Assignment (Terra) (05-Feb-25 - 16-Feb-25); 14: CCCD Assignment (Terra) (05-Feb-25 - 16-Feb-25); 15: CCCD Assignment (Terra) (05-Feb-25 - 16-Feb-25); 16: CCCD Assignment (Terra) (05-Feb-25 - 16-Feb-25)
Solution thinking (Alex, Shifan, Terra, Ryan, Luqman) | 09-Feb-2025 | 17-Feb-2025 | 9: Solution thinking (Alex, Shifan, Terra, Ryan, Luqman) (09-Feb-25 - 17-Feb-25); 10: Solution thinking (Alex, Shifan, Terra, Ryan, Luqman) (09-Feb-25 - 17-Feb-25); 11: Solution thinking (Alex, Shifan, Terra, Ryan, Luqman) (09-Feb-25 - 17-Feb-25); 12: Solution thinking (Alex, Shifan, Terra, Ryan, Luqman) (09-Feb-25 - 17-Feb-25); 13: Solution thinking (Alex, Shifan, Terra, Ryan, Luqman) (09-Feb-25 - 17-Feb-25); 14: Solution thinking (Alex, Shifan, Terra, Ryan, Luqman) (09-Feb-25 - 17-Feb-25); 15: Solution thinking (Alex, Shifan, Terra, Ryan, Luqman) (09-Feb-25 - 17-Feb-25); 16: Solution thinking (Alex, Shifan, Terra, Ryan, Luqman) (09-Feb-25 - 17-Feb-25); 17: Solution thinking (Alex, Shifan, Terra, Ryan, Luqman) (09-Feb-25 - 17-Feb-25)
Product Design (All) | 15-Feb-2025 | 06-Mar-2025 | 15: Product Design (All) (15-Feb-25 - 25-Apr-25); 16: Product Design (All) (15-Feb-25 - 06-Mar-25); 17: Product Design (All) (15-Feb-25 - 06-Mar-25); 18: Product Design (All) (15-Feb-25 - 06-Mar-25); 19: Product Design (All) (15-Feb-25 - 06-Mar-25); 20: Product Design (All) (15-Feb-25 - 06-Mar-25); 21: Product Design (All) (15-Feb-25 - 06-Mar-25); 22: Product Design (All) (15-Feb-25 - 06-Mar-25); 23: Product Design (All) (15-Feb-25 - 06-Mar-25); 24: Product Design (All) (15-Feb-25 - 06-Mar-25); 25: Product Design (All) (15-Feb-25 - 06-Mar-25); 26: Product Design (All) (15-Feb-25 - 06-Mar-25); 27: Product Design (All) (15-Feb-25 - 06-Mar-25); 28: Product Design (All) (15-Feb-25 - 06-Mar-25); 1: Product Design (All) (15-Feb-25 - 06-Mar-25); 2: Product Design (All) (15-Feb-25 - 06-Mar-25); 3: Product Design (All) (15-Feb-25 - 06-Mar-25); 4: Product Design (All) (15-Feb-25 - 06-Mar-25); 5: Product Design (All) (15-Feb-25 - 06-Mar-25); 6: Product Design (All) (15-Feb-25 - 06-Mar-25)
Brochure (Alex, Ryan) | 17-Feb-2025 | 25-Feb-2025 | 17: Brochure (Alex, Ryan) (17-Feb-25 - 25-Feb-25); 18: Brochure (Alex, Ryan) (17-Feb-25 - 25-Feb-25); 19: Brochure (Alex, Ryan) (17-Feb-25 - 25-Feb-25); 20: Brochure (Alex, Ryan) (17-Feb-25 - 25-Feb-25); 21: Brochure (Alex, Ryan) (17-Feb-25 - 25-Feb-25); 22: Brochure (Alex, Ryan) (17-Feb-25 - 25-Feb-25); 23: Brochure (Alex, Ryan) (17-Feb-25 - 25-Feb-25); 24: Brochure (Alex, Ryan) (17-Feb-25 - 25-Feb-25); 25: Brochure (Alex, Ryan) (17-Feb-25 - 25-Feb-25)
Presentation Video (Alex, Shifan Terra) | 2025-03-08 | 2025-03-08
Technical Design Review (Alex, Shifan, Terra) | 2025-03-15 | 2025-03-15 | 15: Technical Design Review (Alex, Shifan, Terra)
Python Project (Shifan) | 2025-03-23 | 2025-04-01 | 23: Python Project (Shifan) (23-Mar-2025 to 1-Apr-2025)
Sketching/Design analysis (Terra) | 2025-04-13 | 2025-04-13 | 13: Sketching/Design analysis (Terra)
CAD work/Onshape (Terra) | 2025-04-14 | 2025-04-24 | 14: CAD work/Onshape(Terra)(14-Apr-25 to 24-Apr-25)
Sheet set up (Terra) | 2025-04-24 | 2025-04-25 | 24: Sheet set up (Terra) (24-Apr-2025 to 25-Apr-2025)
Team Reflection (Alex, Shifan, Terra) | 2025-04-25 | 2025-04-27 | 25: Team Reflection (Alex, Shifan, Terra) (25-Apr-25 to 27-Apr-2025)
Design Notebook (Terra) | 2025-01-30 | 2025-04-25 | 30: Design Notebook (Terra)(20-Jan-25 to 25-Apr-25)
Final Presentation (Alex, Terra, Shifan) | 2025-04-20 | 2025-04-25 | 20: Final Presentation (Alex,Terra,Shifan)(20-Apr-25 to 25-Apr-25)